## Slide 1
STRATEGY REVIEW
FY27 Performance Snapshot
Retail sales tracking ahead of plan through the first quarter. Trained 100 employees across 12 teams, with one proof-of-concept project per team and three winning solutions selected for production. The recommendation is to hold the current roadmap and release the second tranche of budget in November.
104%
TARGET ACHIEVED
100
EMPLOYEES TRAINED
12
TEAMS ENABLED
3
WINNING SOLUTIONS
MC GROUP / EXECUTIVE BRIEF
OCT 2026

## Slide 2
RISKS
What Could Move the Number
Three items sit on the critical path. First, vendor capacity for the Advance workshop must be confirmed by 1 November. Second, the e-commerce channel mix shifted toward marketplace, which carries a higher commission and compresses margin. Third, two functions have not yet named their executive sponsor, which delays their proof-of-concept kickoff into the next quarter.
1 Nov
VENDOR DEADLINE
2
FUNCTIONS UNSPONSORED
MC GROUP / EXECUTIVE BRIEF
OCT 2026

## Slide 3
DECISION REQUESTED
Approve the Second Tranche
The executive is asked to approve the second budget tranche and to confirm one sponsor per function. Approval this week keeps the Advance workshop on schedule and holds the savings captured in the vendor comparison.
80,500
THB SAVED
16.6%
BELOW BASE PROPOSAL
MC GROUP / EXECUTIVE BRIEF
OCT 2026